## Read me
UGC workflow tracker
Free template from the guide at getbriefbase.com/blog/how-to-manage-ugc-creators-without-going-insane
Board: one row per video. Keep every video in exactly one stage. Sort by Next date, not by brand.
Rows turn red when the next date has passed and the video is not marked Paid.
Payments: one row per creator and video. Pay by fills itself in as 7 days after approval; change the formula if your terms differ.
Rows turn red when the pay-by date has passed and Paid on is empty.
Stages: what done means at each stage, and who owns it.
The three example rows on Board and the two on Payments are made up. Delete them before you start.
Opens in Excel, Google Sheets (File, Import) and Numbers.

## Board
Brand | Video | Creator | Stage | Next date | What is due on that date | Owner | Fee (USD) | Paid | Files link | Notes
Example: skincare brand | Serum, hook A | Creator 1 | 4. Product and filming | 2026-10-19 | First cut due (product arrived Oct 12) | Producer | 250 | No |  | Example row: delete before use
Example: skincare brand | Serum, hook B | Creator 2 | 6. Client approval | 2026-10-15 | Client feedback due (round 1 of 2) | Account lead | 250 | No |  | Example row: delete before use
Example: coffee brand | Grinder demo | Creator 3 | 7. Delivery and payment | 2026-10-16 | Pay creator (7 days after approval) | Producer | 300 | No |  | Example row: delete before use

## Payments
Creator | Video | Amount owed | Currency | Approved on | Pay by (approved + 7 days) | Paid on | Method | Payment reference | US creator: Form W-9 on file
Creator 3 | Grinder demo | 300 | USD | 2026-10-09 |  |  | Bank transfer |  | Yes
Creator 2 | Serum, hook B | 250 | USD | [5 empty] | Not US

## Stages
Stage | Owner | Done when
1. Request | Account lead | The brand's ask is written down: product, goal, number of videos, platforms, deadline, budget
2. Brief | Account lead | A one-page brief per video is approved by the brand
3. Creator confirmed | Producer | The creator has accepted the brief, fee, deadline and usage rights in writing
4. Product and filming | Creator | Product received, used, and first cut uploaded by the agreed date
5. Internal review | Producer | The cut matches the brief (hook, must-shows, specs) and every experience claim is true for the creator
6. Client approval | Account lead | The brand approves, or gives timestamped feedback within the agreed revision rounds
7. Delivery and payment | Producer | Final files and raw clips are stored with their usage terms, and the creator is paid